**True schedule and reviewers' comments for eutrophication fact sheet:**

1. All text due from authors on January 6, 2012.

2. January 9: Fact sheet sent to subcommittee for review comments due January 18.

3. January 20: Text sent to Steering Committee for review. Due back on: January 30.

4. February 1: Fact sheet sent to Council Outreach. Comments due on February 8.

5. February 9: Fact sheet sent to data providers (comments due February 17), including: Dan Codiga (URI), Ru Morrison (NERACOOS) and Riley Young Morse (GMRI)

6. Fact sheet sent to Eutrophication for final review before design on February 20. Comments due February 27.

7. Sent to Peggy Issenman on February 28.

8. All data QC'd and in Indicator Reporting Tool (C. Tilburg task)?

9. Sent to Steering Committee for final designed review on March 9. Due back on March 15.

10. Sent to Subcommittee for final designed review March 9. Due back on March 15.

11. March 19: Sent to Management and Finance for final designed review on. Due back March 23.

12. All comments/changes due in. Printing on March 30, 2012.