Theme Paper Process

| Task | Participants | Time frame |
| --- | --- | --- |
| Review of scope of paper and DPSIR framework | Editor and authors | 2 weeks |
| Draft table of contents | Authors | 2 weeks |
| Review of draft table of contents | Editorial Committee | 2 weeks |
| Draft theme paper | Authors | 3 months |
| Editorial Committee and peer review | Peer reviewers Editorial Committee | 2 weeks |
| Authors incorporate review comments | Authors | 2 weeks |
| GOM Working Group and Council Review (Send to Joan LeBlanc for distribution to Working Group and Tim Hall for distribution to sub-group of Council) | GOM Working Group Council sub-group | 2 weeks |
| Authors incorporate review comments and provide Final theme paper | Authors | 2 weeks |
| GOMC Publication protocol (Send to Cindy Krum for compliance with Publication Protocol) | Secretariat/Associations | 1 week |
| Layout | Peter Taylor | 2 weeks |